## Sheet1
Row Labels | Count of Project Status (On-Track, Delayed, Completed, Awaiting Sanction)
Awaiting Sanction | 6
Completed | 1
Delayed | 8
On-Track | 9
Grand Total | 24

## L&U-TSJ
SL. NO. | PROJECT TITLE/ ACTIVITY DESCRIPTION | PROJECT NO. ((R&D, NON-R&D, ASPIRE, Capex Scheme No, Others)/ Product or System under OASA Support | Project Category (Capex, Shikhar, SIP, GB, DM, External) | ABP Strategy No. | KPM | UoM | Capex Scheme Value (in Cr) | AREA | PROFESSIONALS INVOLVED (WRITE '(L)' TO INDICATE THE LEADER) | PLANNED START DATE | PLANNED COMPLETION DATE | ACTUAL COMPLETION DATE | Shikhar Stage (For Shikhar Project) | Project Status (On-Track, Delayed, Completed, Awaiting Sanction) | CURRENT MILESTONE | REMARKS |  | Strategy | KPM | UOM | PQCDSME
1 | DLS system upgrade for JCAPCPL |  | External | 1.2 Upgrade of obsolete systems | No of systems | Nos |  | JCAPCPL | Sambhav Prashit Khapale | May'26 | Dec`26 |  |  | On-Track |  |  | On-Track | 1.1 Improving adverse KPI's in the (2x2 matrix) system framework | % improvement in adverse KPI's | %
2 | CTTS System Upgrade for JCAPCPL | no IC0000000217 | External | 1.2 Upgrade of obsolete systems | No of systems | Nos |  | JCAPCPL | Prashant Kumar/Nikhil Sharma | May'26 | Dec`26 |  |  | On-Track |  |  | Delayed | 1.2 Upgrade of obsolete systems | No of systems | Nos
3 | AIRYMS for Ludhiana Project |  | CAPEX | 1.3 Ensuring time compliance for all customer facing projects in JILE & Other Projects | % of project completion on time | % |  | LUDHIANA | Priya Ranjan Mahapatra/Aditya Gautam | Oct'26 | Jul`26 |  |  | On-Track |  |  | Completed | 1.3 Ensuring time compliance for all customer facing projects in JILE & Other Projects | % of project completion on time | %
4 | Android HHT APP for CYMS TSCR |  | DM | 1.3 Ensuring time compliance for all customer facing projects in JILE & Other Projects | % of project completion on time | % |  | TSCR | Prashant kumar | Sep'26 | Feb`27 |  |  | On-Track |  |  | Awaiting Sanction | 1.4 No of new systems & solutions added in DM for sustenance | No of systems/Projects | Nos
5 | Android HHT APP for CTTS CRM |  | DM | 1.3 Ensuring time compliance for all customer facing projects in JILE & Other Projects | % of project completion on time | % |  | CRM | Nikhil Sharma | Sep'26 | Feb`27 |  |  | On-Track |  |  |  | 1.5 Automation Review Meeting/ Process Insights to Senior Management | Quarterly Review Meeting at Chief Level with Quarterly Report | Nos
6 | Android HHT APP for CTTS CRM BARA |  | DM | 1.3 Ensuring time compliance for all customer facing projects in JILE & Other Projects | % of project completion on time | % |  | CRM-BARA | Priya Ranjan Mohapatra | May'26 | JULY'26 |  |  | On-Track |  |  |  | 1.6 Compliane to OFI from Chiefs KPI | Action Against of OFI | %
7 | Android HHT APP for CTTS JCAPCPL |  | DM | 1.3 Ensuring time compliance for all customer facing projects in JILE & Other Projects | % of project completion on time | % |  | JCAPCPL | Prashant kumar | June'26 | Dec`26 |  |  | On-Track |  |  |  | 2.1 Shikhar Savings in Automation - D4 Value | INR Cr | INR
8 | AI - for REBAR Yard Management |  | DM | 3.1 New Process Optimization Solutions | No. Of solutions | Nos |  | LUDHIANA | Priya Ranjan Mahapatra | June'26 | Sep`26 |  |  | On-Track |  | Continuous addition/deletion/extension |  | 2.2 Savings through improvement (GB+SIP) projects | INR Cr | INR
9 | AI - for CYMS |  | DM | 3.1 New Process Optimization Solutions | No. Of solutions | Nos |  | TSJ-HSM | Prashant kumar | Oct'26 | Nov`26 |  |  | Delayed |  |  |  | 3.1 New Process Optimization Solutions | No. Of solutions | Nos
10 | Auto Delay capture and Line down alarm in CDL1 | SHIKHAR25/IDEA/28375 | DM | 2.1 Shikhar Savings in Automation - D4 Value | INR Cr | INR |  | TSJ-HSM | Sambhav Prashit Kaphle | Apr'26 | May`26 | May'26 |  | Completed |  |  |  | 3.2 Horizontal Deployment of In house solutions - Including 40MnT | No. of Solutions | Nos
11 | Enhancement of CDL 1 AUTOMASS UPDATION |  | DM | 1.3 Ensuring time compliance for all customer facing projects in JILE & Other Projects | % of project completion on time | % |  | TSJ-HSM | Aditya Gautam/Sambhav Prashit Kaphle | Apr'26 | Aug`26 |  |  | On-Track |  |  |  | 3.3 Deployment of Bought - out solutions - Including 40MnT | No. Of solutions | Nos
12 | AI for CTTS |  | DM | 3.1 New Process Optimization Solutions | No. Of solutions | Nos |  | CRM | Nikhil Sharma | Nov'26 | Dec`26 |  |  | Delayed |  |  |  | 3.4 Deployment of System Integration & IOT solutions. | No. Of solutions | Nos
13 | CO-IOT coverage for TSL |  | DM | 1.4 No of new systems & solutions added in DM for sustenance | No of systems/Projects | Nos |  | TSI | Urvashi Kumari Chaudhury | June'26 | Dec`26 |  |  | Awaiting Sanction |  |  |  | 4.1 Publication/ acceptance of papers in international journals | Papers accepted | Nos
14 | Copilot: Asset Management Prescriptive model for anomalies detected in rotating equipment |  | SHIKHAR | 3.1 New Process Optimization Solutions | No. Of solutions | Nos | TBD | TSJ | nikhil sharma/Sambhav | April'26 | Dec`26 |  |  | Delayed |  |  |  | 4.2 Acceptance of papers in inhouse journals and conferences/seminars | Papers accepted | Nos
15 | HML INTEGRATED EYE | SHIKHAR25/IDEA/27674 | SHIKHAR | 2.1 Shikhar Savings in Automation - D4 Value | INR Cr | INR | TBD | TSJ | Aditya Gautam/Urvashi Kumari Chaudhury | April'26 | Dec`26 |  |  | Awaiting Sanction |  |  |  | 4.3 Submission of patents / copyrights to TSL, IP Cell | Patents/copyrights submitted | Nos
16 | Development of algorithms for Remote Dynamic Balancing based on coefficient of influence for fans (other than Vessel ID Fan, where there is requirement of mass addition). |  | DMAIC | 3.1 New Process Optimization Solutions | No. Of solutions | Nos |  | TSJ | Sambhav/Nikhil | Jul'26 | Dec`27 |  |  | Delayed |  |  |  | 4.4 New Prototypes developed (Projects under R&D Corpus) | Number of projects | Nos
17 | Detection of periodic frequency components in vibration spectrum & matching with known defect frequency |  | DMAIC | 3.1 New Process Optimization Solutions | No. Of solutions | Nos |  | TSJ | Sambhav/Nikhil | Oct'26 | Jan`27 |  |  | Awaiting Sanction |  |  |  | 4.5 Exploration of technologies relevant for Steel industry | Technologies explored | Nos
18 | AIRYMS for NINL |  | CAPEX | 3.2 Horizontal Deployment of In house solutions - Including 40MnT | No. of Solutions | Nos |  | NINL | Priya Ranjan Mahapatra/Aditya Gautam | Dec'26 | Feb`27 |  |  | Delayed |  |  |  | 4.5 80% of Automation Involved in AI/VA/ML projects | No Of Professionals Leading AI Projects | Nos
19 | CTTS for TCIL |  | CAPEX | 3.2 Horizontal Deployment of In house solutions - Including 40MnT | No. of Solutions | Nos |  | TCIL | Nikhil shama/Prashant Kumar | Dec'26 | Feb`27 |  |  | Awaiting Sanction |  |  |  | 4.6 Research & Innovation accolades (Innovista, BRICS, ANQ etc) | Number of accolades | Nos
20 | CTTS for CRCW extension(HRPGL) |  | CAPEX | 3.2 Horizontal Deployment of In house solutions - Including 40MnT | No. of Solutions | Nos |  | CRCW | Prashant Kumar | May'26 | Feb`27 |  |  | Delayed |  |  |  | 4.7 Technical upskilling - through Provided platforms (EdNext ) -No of hours, 100 %Coverage. | No of Hours | Nos
21 | SRT - New IOT Device Configuration, Dashboard and alert |  | DM | 3.4 Deployment of System Integration & IOT solutions. | No. Of solutions | Nos |  | TSJ | Avir Mondal | Nov'26 | Feb`27 |  |  | Awaiting Sanction |  |  |  | 5.1 Compliance to Annexure- 9 audit of contractors | % Compliance | %
22 | CO -IOT Gas sensor across location Configuration and Dashboard and alert management |  | DM | 3.4 Deployment of System Integration & IOT solutions. | No. Of solutions | Nos |  | TSI | Urvashi Kumari Chaudhury | June'26 | Nov`27 |  |  | Delayed |  |  |  | 5.2 Compliance to identified EHSMP& Environment projects | % compliance | %
23 | Temperature-Humidity IOT sensor Configuration, Dashboard and alert |  | DM | 3.4 Deployment of System Integration & IOT solutions. | No. Of solutions | Nos |  | TSI | Urvashi Kumari Chaudhury | April'26 | Feb`27 |  |  | Awaiting Sanction |  |  |  | Departmental AIC Meetings | No Of GEMBA & Line Walks | Nos
|  |  |  | 2.1 Shikhar Savings in Automation - D4 Value | INR Cr | INR
24 | indigenous IOT vibration Sensor Configuration, Dashboard Model and alert |  | DM | 3.4 Deployment of System Integration & IOT solutions. | No. Of solutions | Nos |  | TSI | nikhil sharma/Sambhav | April'26 | Feb`27 |  |  | Delayed |  |  |  | 5.3 E Permit & CWF Compliance | 100%
[18 empty] | 5.4 Cross Functional Visit (4 Nos per month) | No of Visit/Gemba & Line Walks | Nos
[18 empty] | 6.1 - TFS usage compliance (For Inhouse Soln) To be Merged with 6.2, 6.2 shall remain | % compliance | %
[18 empty] | 6.2 - Implementation of SQA index for all JILE projects (Project milestones compliance) | SQA score | % score
[18 empty] | 6.3Compliance to TSL audits (internal DM & external). | % compliance | %
[18 empty] | 6.4 Compliance to Data Office Initiatives (Ex Sensor to SAPS reports ) KPI & KPM to be discussed (90% of auto posting of Data to SAP through Pipeline ) | % compliance | %
[18 empty] | 7.1 Appreciation through Steel Icons | Budget utilization | %
[18 empty] | 7.2 Appreciation through Shabaash | Budget utilization | %
[18 empty] | 7.3 Volunteerism - Portal of Purpose ( 4 hrs login/professional) | % Compliance | Nos
[18 empty] | 7.4 Get together for Fun &Team building activities | No of sessions | Nos
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Move to Different Strategy
Note on V10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be Kept
Note on V21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Disuss with JMK for dropping
Note on V31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Discuss KPI & KPM To be Kept

## Activity Plan & DOW sample
Activity Plan and DOW sample format Agencies:- Scheme Owner, Scheme Executors, Procurement, BU, Vendor
No | ACTIVITIES LIST (List of Activities from Project Plan Document (Development Methodology) & Quality Plan) |  | From Date of Sanction of Scheme | [47 empty] | RESPONSIBILITY
|  |  | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  | M7 |  |  |  | M8 |  |  |  | M9 |  |  |  | M10 |  |  |  | M11 |  |  |  | M12 |  |  |  | Vendor | HML | EQMS | AUT
|  | WEEK | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Scheme Sanction RFQ AND P.O. | P | [48 empty] | Offer | A | R | P
A
| DOCUMENTATION BY VENDOR | [49 empty] | P
2 | LOCO ELECTRONICS | P | [48 empty] | P |  | A | A
A
3 | HAND HELD REMOTE | P | [48 empty] | P | A | A | A
A
4 | INSTALLATION SCHEDULE | P | [48 empty] | P | A | A | A
A
5 | FMEA , SAFETY & OPN | P | [48 empty] | P | C | A | A
A
6 | DELIVERY OF ITEMS | P | [48 empty] | Part Delivery in 3/4 phases | R | R | R
A
| INSTALLATION(See Schedule) | [49 empty] | See Installation Schedule
7 | CLEARANCES AND PERMITS | P | [48 empty] | P | A | A
A
8 | LOCO DRIVE INTERFACE | P | [50 empty] | P/R
A
9 | TX/RX | P | [50 empty] | A | A
A
10 | FAT | P | [49 empty] | A | A | A
A
11 | COMMISSIONING & Handover | [49 empty] | 3/4 Loco every phase | C | A | A
12 | TRAINING | P | [48 empty] | AS PER PO | R
|  | A | [48 empty] | AS PER PO | C
13 | AMC | P | [48 empty] | Existing AMC /CMC | A | Daily Management /Certify | CAPA/ MOC
A
| P- PLANNED | A-Actual
| 1.LD clauses to be incorporated in the P.O. 2.Longer Lead time requested by Vendor due to import of several components . 3.Phased Delivery and Payment to vendor on Milestone completion 4.AMC order in place after successful commissioning. | [49 empty] | LEGENDS:- P- PREPARE & SUPPLY A - APPROVE C- CERTIFY R- REVIEW AMC/CMC- ANNUAL OR COMPREHENSIVE MAINTENANCE CONTRACT
|  | Month | Plan |  | Actual
|  |  | Nos | % | Nos | %
|  | M1 | 0 | 0 | 0 | 0
|  | M2 | 1 | 7.6923 | 1 | 7.6923
|  | M3 | 4 | 30.7692 | 0 | 0
|  | M4 | 0 | 0 | 0 | 0
|  | M5 | 0 | 0 | 0 | 0
|  | M6 | 0 | 0 | 0 | 0
|  | M7 | 1 | 7.6923 | 1 | 8
|  | M8 | 1 | 7.6923 | 0 | 0
|  | M9 | 2 | 15.3846 | 3 | 24
|  | M10 | 1 | 7.6923
|  | M11 | 2 | 15.3846
|  | M12 | 1 | 7.6923
|  |  | 13 | 100 | 5 | 40