## WBS Details
WBS Details | Plan Start | Plan End | Actual Start | Actual End | Planned Days | Actual Days | Delivered | % Complete | Duration
Project Initiation | 24-Sep-2026 | 13-Oct-2026 | 24-Sep-2026 | 21-Oct-2026 | 19 | 27 | N | 30 | 0
Requirement Analysis | 22-Jun-2026 | 04-Sep-2026 | 22-Jun-2026 | 14-Sep-2026 | 74 | 84 | N | 50 | 0
Project Planning | 09-May-2026 | 29-Jul-2026 | 09-May-2026 | 08-Aug-2026 | 81 | 91 | N | 30 | 0
Project Plan | 03-Jul-2026 | 02-Sep-2026 | 03-Jul-2026 | 29-Aug-2026 | 61 | 57 | N | 50 | 0
Resource Plan | 30-Jul-2026 | 01-Oct-2026 | 30-Jul-2026 | 09-Oct-2026 | 63 | 71 | N | 80 | 0
Project Schedule | 25-Aug-2026 | 01-Oct-2026 | 25-Aug-2026 | 17-Oct-2026 | 37 | 53 | N | 80 | 0
Expenditure Plan | 04-Jun-2026 | 16-Aug-2026 | 04-Jun-2026 | 04-Sep-2026 | 73 | 92 | Yes | 100 | 0
Design | 05-Aug-2026 | 25-Aug-2026 | 05-Aug-2026 | 07-Sep-2026 | 20 | 33 | Yes | 50 | 0
Functional Specification | 04-Jun-2026 | 13-Jul-2026 | 04-Jun-2026 | 17-Jul-2026 | 39 | 43 | N | 50 | 0
Global Design | 20-Jul-2026 | 13-Oct-2026 | 20-Jul-2026 | 22-Oct-2026 | 85 | 94 | N | 100 | 0
Detail Design | 17-May-2026 | 14-Aug-2026 | 17-May-2026 | 19-Aug-2026 | 89 | 94 | Yes | 50 | 0
Program Specification | 14-Aug-2026 | 28-Sep-2026 | 14-Aug-2026 | 24-Sep-2026 | 45 | 41 | Yes | 100 | 0
UI/L2 Interface Conversion | 17-Jul-2026 | 10-Aug-2026 | 17-Jul-2026 | 22-Aug-2026 | 24 | 36 | Yes | 50 | 0
Project Execution | 07-Aug-2026 | 02-Nov-2026 | 07-Aug-2026 | 08-Nov-2026 | 87 | 93 | Yes | 30 | 0
Procurement | 25-May-2026 | 04-Aug-2026 | 25-May-2026 | 04-Aug-2026 | 71 | 71 | Yes | 80 | 0
Coding | 19-Aug-2026 | 26-Oct-2026 | 19-Aug-2026 | 04-Nov-2026 | 68 | 77 | Yes | 80 | 0
Unit Testing | 06-Jun-2026 | 26-Aug-2026 | 06-Jun-2026 | 26-Aug-2026 | 81 | 81 | Yes | 80 | 0
Integration Testing | 25-Aug-2026 | 17-Oct-2026 | 25-Aug-2026 | 17-Oct-2026 | 53 | 53 | Yes | 50 | 0
Project Closing | 31-Aug-2026 | 29-Oct-2026 | 31-Aug-2026 | 03-Nov-2026 | 59 | 64 | N | 50 | 0
Final Design | 02-May-2026 | 25-Jul-2026 | 02-May-2026 | 11-Aug-2026 | 84 | 101 | Yes | 80 | 0
Final Code | 21-Jul-2026 | 05-Sep-2026 | 21-Jul-2026 | 02-Sep-2026 | 46 | 43 | N | 100 | 0
Learning | 12-Aug-2026 | 09-Nov-2026 | 12-Aug-2026 | 09-Nov-2026 | 89 | 89 | N | 100 | 0
Closing Report | 01-Jul-2026 | 21-Sep-2026 | 01-Jul-2026 | 24-Sep-2026 | 82 | 85 | N | 100 | 0

## Import Projects
Project Name | Tasks | Plan Start | Plan End | Status
Project Initiation | Requirement Analysis | 22-Jun-2026 | 04-Sep-2026 | IN_PROGRESS
Project Planning | Project Plan | 03-Jul-2026 | 02-Sep-2026 | IN_PROGRESS
Project Planning | Resource Plan | 30-Jul-2026 | 01-Oct-2026 | IN_PROGRESS
Project Planning | Project Schedule | 25-Aug-2026 | 01-Oct-2026 | IN_PROGRESS
Project Planning | Expenditure Plan | 04-Jun-2026 | 16-Aug-2026 | COMPLETED
Design | Functional Specification | 04-Jun-2026 | 13-Jul-2026 | IN_PROGRESS
Design | Global Design | 20-Jul-2026 | 13-Oct-2026 | COMPLETED
Design | Detail Design | 17-May-2026 | 14-Aug-2026 | IN_PROGRESS
Design | Program Specification | 14-Aug-2026 | 28-Sep-2026 | COMPLETED
Design | UI/L2 Interface Conversion | 17-Jul-2026 | 10-Aug-2026 | IN_PROGRESS
Project Execution | Procurement | 25-May-2026 | 04-Aug-2026 | IN_PROGRESS
Project Execution | Coding | 19-Aug-2026 | 26-Oct-2026 | IN_PROGRESS
Project Execution | Unit Testing | 06-Jun-2026 | 26-Aug-2026 | IN_PROGRESS
Project Execution | Integration Testing | 25-Aug-2026 | 17-Oct-2026 | IN_PROGRESS
Project Closing | Final Design | 02-May-2026 | 25-Jul-2026 | IN_PROGRESS
Project Closing | Final Code | 21-Jul-2026 | 05-Sep-2026 | COMPLETED
Project Closing | Learning | 12-Aug-2026 | 09-Nov-2026 | COMPLETED
Project Closing | Closing Report | 01-Jul-2026 | 21-Sep-2026 | COMPLETED